## Cloud Risk Assessment
Care Access Navigator — Cloud Security 1 Criterion 1: Five-Risk NIST-Style Cloud Risk Assessment
Prepared 09/16/2026 ¦ Same column structure as the capstone's existing risk register, so these rows append directly
Legend: Likelihood and Impact are scored 1 (Low) – 3 (High). Risk Score = Likelihood × Impact. Rating auto-calculates: 1–2 Low, 3–4 Medium, 6–9 High.
Risk ID | Risk Description | Category | Likelihood (1-3) | Impact (1-3) | Risk Score | Inherent Risk Rating | Mitigation / Control | Risk Owner | Status
CR-01 | Storage account/container misconfigured to allow public read access | Data Exposure | 1 | 3 | 3 | Medium | Block Public Access enforced on cloudsec1-evidence; Azure Policy alert if a container's anonymous access level changes | Akhila Chennamaneni | Mitigated (configured 09/14/2026)
CR-02 | Over-permissive Entra ID / IAM role assignment grants broader access than a role requires | Access Control | 2 | 3 | 6 | High | Least-privilege custom policies per RBAC role; periodic access review (ties to capstone Week 4) | Akhila Chennamaneni | Planned
CR-03 | Unpatched Azure VM hosting the EHR Simulator/Patient Portal stand-in | Infrastructure | 2 | 2 | 4 | Medium | Enable automated patching (Azure Update Manager); host firewall in addition to NSG | Akhila Chennamaneni | Planned
CR-04 | Vulnerable base image used in the containerized EHR Simulator/Patient Portal app | Application Security | 2 | 2 | 4 | Medium | Trivy scan before deploy; pinned, minimal base image versions | Akhila Chennamaneni | Planned
CR-05 | Entra ID user/service account without MFA enabled | Identity | 2 | 3 | 6 | High | MFA enforced via Conditional Access policy on all accounts in the tenant | Akhila Chennamaneni | Planned
Evidence on file: screenshots supporting CR-01 (Block Public Access), CR-05 (Conditional Access MFA policy); CR-02–CR-04 close out as Criteria 2–4 of this rubric are completed.