## Dashboard
Care Access Navigator — Compliance Monitoring Dashboard
Live formulas: statuses recalculate from the KPI Monitor and Remediation sheets (update 'Current'
and '% complete' values). Last data refresh: 2026-10-13.
| KPI (percent) | Current | Target
KPIs Green | K-01 Asset tagging compliance |  | 100
KPIs Amber | K-02 Guardrail policy compliance |  | 100
KPIs Red | K-03 Least-privilege accounts |  | 100
Open findings | K-04 MFA coverage (privileged + CDE) |  | 100
Open High findings | K-05 Security alert rules enabled |  | 100
Findings overdue (Red) | K-06 Log retention vs requirement |  | 100
| K-07 Audit test pass rate |  | 90

## KPI Monitor
ID | KPI | Definition / formula | Target | Amber threshold | Current | Unit | Status | Source | Frequency | Owner | Measurement note
K-01 | Asset tagging compliance | Resources + RGs with all 3 mandatory tags / total | 100 | 95 | 100 | % |  | Azure Resource Graph | Daily (Azure Policy) | GRC Analyst | Measured 2026-10-13: 19/19
K-02 | Guardrail policy compliance | Compliant evaluations / total for can-guardrails | 100 | 95 | 100 | % |  | Azure Policy | Daily | Security Officer | Measured 2026-10-08: 31/31
K-03 | Least-privilege accounts | Workforce accounts holding exactly one approved role / total | 100 | 95 | 100 | % |  | Keycloak extract | Quarterly | IAM Analyst | Measured 2026-10-13: 9/9
K-04 | MFA coverage (privileged + CDE) | In-scope accounts forced through MFA / in-scope accounts | 100 | 90 | 0 | % |  | Keycloak flows | Monthly | IAM Analyst | Measured 2026-10-13: flow not bound
K-05 | Security alert rules enabled | Enabled alert rules / defined alert rules | 100 | 90 | 100 | % |  | Azure Monitor | Weekly | Security Analyst | Measured 2026-10-13: 7/7
K-06 | Log retention vs requirement | Days of centrally retained logs / 365 | 100 | 50 | 24.7 | % |  | Log platform | Monthly | Security Officer | Measured 2026-10-13: 90/365
K-07 | Audit test pass rate | Passed audit tests / tests performed | 90 | 75 | 53.3 | % |  | Audit CAN-IA-2026-01 | Per audit | GRC Analyst | Measured 2026-10-13: 8/15
K-08 | High findings overdue | Open High findings past target date | 0 | 1 | 0 | count |  | Remediation tracker | Weekly | GRC Analyst | Measured 2026-10-13
K-09 | Mean time to detect (MTTD) | Avg minutes from security event to alert | 15 | 30 | 7.5 | min |  | Incident records | Per incident | Security Analyst | INC-20261008-01
K-10 | Workforce training completion | Workforce who completed required modules / workforce | 95 | 85 |  | % |  | LMS | Monthly | Privacy Officer | Starts Mar 2027 (baseline pending)
K-11 | Access reviews completed on time | Reviews certified by deadline / reviews due | 95 | 85 |  | % |  | Review tickets | Quarterly | IAM Analyst | First review due 2026-12-15

## Remediation
ID | Finding | Rating | Requirement | Owner | Target date | % complete | RAG status | Last update | Evidence | Notes
F-01 | MFA not enforced for privileged / CDE access | High | HIPAA 164.312(d); PCI 8.4.2 | IAM Analyst | 2026-11-06 | 0% |  | 2026-10-13 | E-AC-02
F-02 | Account lockout (brute-force protection) disabled | High | PCI 8.3.4 | IAM Analyst | 2026-10-23 | 0% |  | 2026-10-13 | E-AC-02
F-03 | No 12-month central log retention | High | HIPAA 164.312(b); PCI 10.5.1 | Security Officer | 2026-11-30 | 0% |  | 2026-10-13 | E-LOG-01
F-04 | Password length 10 / history 3 below PCI minimum | Medium | PCI 8.3.6, 8.3.7 | IAM Analyst | 2026-10-23 | 0% |  | 2026-10-13 | E-AC-02
F-05 | No completed access review / daily log review records | Medium | PCI 7.2.4, 10.4.1 | IAM / Security Analyst | 2026-12-15 | 10% |  | 2026-10-13 | Inquiry
F-06 | Identity provider over HTTP in lab | Low | HIPAA 164.312(e)(1); PCI 4.2.1 | IT Support | 2027-01-31 | 0% |  | 2026-10-13 | E-ENC-01
Rules:
Closed = 100% complete and evidence verified by GRC. Red = past target date. Amber = due within 7 days and under 75% complete. Owners update weekly; committee reviews monthly.
Formulas:
RAG status = IF(G2>=1,"Closed",IF(TODAY()>[Target date],"Red",IF(AND([Target date]-TODAY()<=7,G2<0.75),"Amber","Green")))

## Evidence Register
Evidence ID | File | SHA-256 | Bytes | Collected | Collected by | Location
E-AC-01 | E-AC-01_keycloak_users_roles.txt | 2c94fabfceacd3d058be40bc48ef244f72e9cc218c5826a955f596de522722c1 | 1870 | 2026-10-13 | GRC Analyst | audit-evidence/
E-AC-02 | E-AC-02_authn_settings_and_entra_assignments.txt | eec9ece839fcd29226eef5c7f07343d0873457cdd726aefb5bff71036eb3488f | 993 | 2026-10-13 | GRC Analyst | audit-evidence/
E-ENC-01 | E-ENC-01_tls_enforcement.txt | 2dda385fbcbb32909e5224ccefa8505c617bb346a64f92f45561a0fee09cf668 | 721 | 2026-10-13 | GRC Analyst | audit-evidence/
E-LOG-01 | E-LOG-01_alerting_and_log_retention.txt | 0063a1a5ac8512a10f02f2a3ff109a8f1341adec43d75db22b5fe9d6ea103dc3 | 1665 | 2026-10-13 | GRC Analyst | audit-evidence/
tpl-http | tpl-http.json | 8b114dea7f87a51f1ef7ff76d8e0b95bf8a72a165648b7bdc1cc5ae2ce356c70 | 511 | 2026-10-13 | GRC Analyst | audit-evidence/
tpl-ok | tpl-ok.json | a613a68c745029d5cc7cabbc7cff2a18e3b812e62efa748aca987abc1eb35480 | 508 | 2026-10-13 | GRC Analyst | audit-evidence/
tpl-tls10 | tpl-tls10.json | 6b7d76b0692fef6fd3ffeef9e62ac058cc9d57ccb7463ac386bc6427de021643 | 509 | 2026-10-13 | GRC Analyst | audit-evidence/

## Retention Schedule
Record type | Regulation / driver | Retention | Storage | Access | Owner | Disposal
Compliance policies, procedures (all versions) | HIPAA 164.316(b)(2)(i) | 6 years from last effective date | Policy portal (versioned) | All staff read; GRC edit | GRC Analyst | Secure delete after review
Risk analyses and risk register | HIPAA 164.316(b)(2)(i); 164.308(a)(1) | 6 years | GRC repository | Compliance team | GRC Analyst | Secure delete
Audit reports and evidence packs | HIPAA 164.316; Internal Audit standards | 6 years | Evidence repository (WORM) | Compliance + Internal Audit | Internal Audit | Secure delete
Security audit logs (CDE) | PCI DSS 10.5.1 | 12 months (3 months online) | Central log platform | Security team (read-only) | Security Officer | Automatic expiry
Security audit logs (ePHI systems) | HIPAA 164.312(b) (policy-set) | 6 years (summaries); 12 months raw | Central log platform + archive | Security team | Security Officer | Automatic expiry
Access requests, reviews, certifications | HIPAA 164.308(a)(4); PCI 7.2.4 | 6 years | Ticketing + evidence repository | IAM + managers | IAM Analyst | Secure delete
Training records and attestations | HIPAA 164.530(b)(2), 164.530(j) | 6 years | LMS | HR + Privacy | Privacy Officer | LMS purge
Incident and breach records, notifications | HIPAA 164.530(j); 164.414 burden of proof | 6 years | Incident system | Privacy + Security | Privacy Officer | Secure delete
Business associate agreements | HIPAA 164.316, 164.504(e) | 6 years after termination | Contract system | Legal + Vendor Mgr | Vendor Manager | Secure delete
Medical records (EHR) | NY 10 NYCRR 405.10 | 6 years after discharge, or 3 years after age 18, whichever is longer | EHR system | Clinical roles (RBAC) | HIM Director | NIST SP 800-88 purge
PCI SAQ, AOC, ASV scan reports | PCI DSS 12.4, 11.3.2 | 3 years (policy-set) | Compliance repository | Security + Compliance | Security Officer | Secure delete

## Document Register
Doc ID | Title | Version | Owner | Approver | Effective | Next review | Distribution | Classification | Location
CAN-COMP-RA-001 | Compliance Requirements Analysis | 1.0 | GRC Analyst | CCO | 2026-10-13 | 2027-10-13 | Committee, control owners | Internal | Task 1 PDF
CAN-COMP-PLN-001 | Compliance Program Plan FY2027 | 1.0 | CCO | Program Sponsor | 2026-11-01 | 2027-10-01 | Committee, Board | Internal | Task 1 PDF
CAN-COMP-GOV-001 | Compliance Governance Charter & Communication Plan | 1.0 | CCO | Board committee | 2026-11-01 | 2027-11-01 | Committee, Board | Internal | Task 2 PDF
CAN-POL-AC-001 | Access Control and Identity Management Policy | 1.0 | Security Officer | Committee + COO | 2026-12-01 | 2027-12-01 | All workforce, vendors | Internal | Task 2 PDF
CAN-PRC-AC-002 | Quarterly User Access Review Procedure | 1.0 | IAM Analyst | Security Officer | 2027-01-01 | 2028-01-01 | IAM, managers, GRC | Internal | Task 2 PDF
CAN-TRN-PLN-001 | Compliance Training Plan | 1.0 | Privacy Officer | CCO | 2027-01-01 | 2028-01-01 | HR, managers | Internal | Task 2 PDF
CAN-AUD-2026-01 | Internal Compliance Audit Report (IAM & monitoring) | 1.0 | GRC Analyst | Internal Audit | 2026-10-20 | Follow-up Jan 2027 | Committee, Board | Confidential | Task 3 PDF
CAN-RPT-STS-Q4 | Compliance Status Report Q4 2026 | 1.0 | CCO | Program Sponsor | 2026-10-20 | Quarterly | Executives, Board | Confidential | Task 4 PDF
CAN-REC-RET-001 | Records Retention Schedule | 1.0 | GRC Analyst | CCO | 2026-11-01 | 2027-11-01 | All record owners | Internal | Task 4 PDF / tracker
CAN-PLB-IR-001 | Incident Response Playbook | 1.0 | Security Officer | CCO | 2026-10-08 | 2027-10-08 | Security, Privacy, IT | Confidential | CloudSec1 can-secops
CAN-LGL-OBL-001 | Compliance Obligations Matrix | 1.0 | Privacy Officer | CCO + counsel | 2026-11-01 | 2027-11-01 | Compliance team | Internal | Task 5 PDF