## akhila's project board
Akhila's Project Board
Care_Access_Navigator_IAM_GRC
Name | Subitems | Status | Person | Date | Timeline - Start | Timeline - End | Text | Checkbox | Item ID (auto generated)
Empty | [8 empty] | 12760460635
Week 1 — Planning & Healthcare Security Foundations | [8 empty] | 12760460636
Name |  | Others | [6 empty] | 12760460638
Not Started ¦ Monday — Define healthcare scenario and project charter |  | Others |  | 2026-08-17 |  |  |  |  | 12760460640
Not Started ¦ Tuesday — Build requirements matrix and asset inventory |  | Others |  | 2026-08-18 |  |  |  |  | 12760460641
Not Started ¦ Wednesday — Establish risk and compliance foundation |  | Others |  | 2026-08-19 |  |  |  |  | 12760460642
Not Started ¦ Thursday — Create architecture v1 and project backlog |  | Others |  | 2026-08-20 |  |  |  |  | 12760460643
Empty | [8 empty] | 12760460644
Week 2 — Foundation Infrastructure & IAM Lab | [8 empty] | 12760460645
Name |  | Others | [6 empty] | 12760460646
Not Started ¦ Monday — Establish lab workspace and security boundaries |  | Others |  | 2026-08-24 |  |  |  |  | 12760460647
Not Started ¦ Tuesday — Configure Keycloak IAM foundation |  | Others |  | 2026-08-25 |  |  |  |  | 12760460648
Not Started ¦ Wednesday — Define Entra ID identity governance design |  | Others |  | 2026-08-26 |  |  |  |  | 12760460649
Not Started ¦ Thursday — Establish applications, roles, and logging foundation |  | Others |  | 2026-08-27 |  |  |  |  | 12760460650
Empty | [8 empty] | 12760460651
Week 3 — IAM Architecture & RBAC | [8 empty] | 12760460652
Name |  | Others | [6 empty] | 12760460653
Not Started ¦ Monday — Design healthcare RBAC model |  | Others |  | 2026-08-31 |  |  |  |  | 12760460654
Not Started ¦ Tuesday — Apply least privilege and separation-of-duties rules |  | Others |  | 2026-09-01 |  |  |  |  | 12760460852
Not Started ¦ Wednesday — Design access request and approval workflow |  | Others |  | 2026-09-02 |  |  |  |  | 12760460853
Not Started ¦ Thursday — Implement and test RBAC roles |  | Others |  | 2026-09-03 |  |  |  |  | 12760470651
Empty | [8 empty] | 12760470652
Week 4 — Identity Lifecycle | [8 empty] | 12760470653
Name |  | Others | [6 empty] | 12760470654
Not Started ¦ Monday — Design and test Joiner onboarding workflow |  | Others |  | 2026-09-07 |  |  |  |  | 12760470655
Not Started ¦ Tuesday — Execute Mover role-change scenario |  | Others |  | 2026-09-08 |  |  |  |  | 12760470656
Not Started ¦ Wednesday — Execute Leaver deprovisioning scenario |  | Others |  | 2026-09-09 |  |  |  |  | 12760470658
Not Started ¦ Thursday — Perform sample access review and remediation |  | Others |  | 2026-09-10 |  |  |  |  | 12760470660
Empty | [8 empty] | 12760470663
Week 5 — Authentication & Privileged Access | [8 empty] | 12760470666
Name |  | Others | [6 empty] | 12760470668
Not Started ¦ Monday — Document authentication control baseline |  | Others |  | 2026-09-14 |  |  |  |  | 12760448611
Not Started ¦ Tuesday — Build privileged access matrix |  | Others |  | 2026-09-15 |  |  |  |  | 12760448613
Not Started ¦ Wednesday — Define service and vendor identity controls |  | Others |  | 2026-09-16 |  |  |  |  | 12760448615
Not Started ¦ Thursday — Test authentication and privileged-access controls |  | Others |  | 2026-09-17 |  |  |  |  | 12760448618
Empty | [8 empty] | 12760448620
Week 6 — SIEM & Security Monitoring | [8 empty] | 12760448623
Name |  | Others | [6 empty] | 12760448625
Not Started ¦ Monday — Define SIEM monitoring use cases |  | Others |  | 2026-09-21 |  |  |  |  | 12760448627
Not Started ¦ Tuesday — Ingest or generate safe authentication/access events |  | Others |  | 2026-09-22 |  |  |  |  | 12760448630
Not Started ¦ Wednesday — Build identity detection rules and queries |  | Others |  | 2026-09-23 |  |  |  |  | 12760465387
Not Started ¦ Thursday — Build alert severity and triage procedure |  | Others |  | 2026-09-24 |  |  |  |  | 12760465388
Empty | [8 empty] | 12760465389
Week 7 — Incident Detection & Response | [8 empty] | 12760465390
Name |  | Others | [6 empty] | 12760465391
Not Started ¦ Monday — Launch simulated ePHI access incident |  | Others |  | 2026-09-28 |  |  |  |  | 12760465392
Not Started ¦ Tuesday — Investigate identity and application evidence |  | Others |  | 2026-09-29 |  |  |  |  | 12760465393
Not Started ¦ Wednesday — Contain access and document recovery actions |  | Others |  | 2026-09-30 |  |  |  |  | 12760465394
Not Started ¦ Thursday — Complete root cause and lessons learned |  | Others |  | 2026-10-01 |  |  |  |  | 12760465404
Empty | [8 empty] | 12760465405
Week 8 — GRC Risk Assessment | [8 empty] | 12760465406
Name |  | Others | [6 empty] | 12760465407
Not Started ¦ Monday — Define risk scoring and treatment methodology |  | Others |  | 2026-10-05 |  |  |  |  | 12760465408
Not Started ¦ Tuesday — Build IAM/GRC risk register |  | Others |  | 2026-10-06 |  |  |  |  | 12760465409
Not Started ¦ Wednesday — Score inherent and residual risk |  | Others |  | 2026-10-07 |  |  |  |  | 12760465411
Not Started ¦ Thursday — Create risk treatment plan |  | Others |  | 2026-10-08 |  |  |  |  | 12760465412
Empty | [8 empty] | 12760474229
Week 9 — Controls & Compliance Mapping | [8 empty] | 12760474230
Name |  | Others | [6 empty] | 12760474231
Not Started ¦ Monday — Create project control inventory |  | Others |  | 2026-10-12 |  |  |  |  | 12760474232
Not Started ¦ Tuesday — Map controls to HIPAA Security Rule concepts |  | Others |  | 2026-10-13 |  |  |  |  | 12760470454
Not Started ¦ Wednesday — Map controls to NIST framework concepts |  | Others |  | 2026-10-14 |  |  |  |  | 12760470455
Not Started ¦ Thursday — Perform control gap assessment |  | Others |  | 2026-10-15 |  |  |  |  | 12760470456
Empty | [8 empty] | 12760448241
Week 10 — Evidence, Exceptions & Remediation | [8 empty] | 12760448242
Name |  | Others | [6 empty] | 12760448243
Not Started ¦ Monday — Organize control evidence repository |  | Others |  | 2026-10-19 |  |  |  |  | 12760448244
Not Started ¦ Tuesday — Execute sample control tests |  | Others |  | 2026-10-20 |  |  |  |  | 12760448245
Not Started ¦ Wednesday — Create exception register |  | Others |  | 2026-10-21 |  |  |  |  | 12760448246
Not Started ¦ Thursday — Track corrective actions to verification |  | Others |  | 2026-10-22 |  |  |  |  | 12760448247
Empty | [8 empty] | 12760448248
Week 11 — GRC Dashboard & Reporting | [8 empty] | 12760448249
Name |  | Others | [6 empty] | 12760448250
Not Started ¦ Monday — Define dashboard KPIs and reporting design |  | Others |  | 2026-10-26 |  |  |  |  | 12760448251
Not Started ¦ Tuesday — Build IAM metrics dataset |  | Others |  | 2026-10-27 |  |  |  |  | 12760448252
Not Started ¦ Wednesday — Build GRC and incident metrics dataset |  | Others |  | 2026-10-28 |  |  |  |  | 12760448253
Not Started ¦ Thursday — Build and validate integrated Tableau dashboard |  | Others |  | 2026-10-29 |  |  |  |  | 12760448254
Empty | [8 empty] | 12760448255
Week 12 — Testing, Documentation & 5-Minute Demo | [8 empty] | 12760448353
Name |  | Others | [6 empty] | 12760448354
Not Started ¦ Monday — Execute final end-to-end testing |  | Others |  | 2026-11-02 |  |  |  |  | 12760472812
Not Started ¦ Tuesday — Finalize portfolio documentation set |  | Others |  | 2026-11-03 |  |  |  |  | 12760472813
Not Started ¦ Wednesday — Build and rehearse 5-minute capstone demo |  | Others |  | 2026-11-04 |  |  |  |  | 12760472815
Not Started ¦ Thursday — Present project, close work, and capture lessons learned |  | Others |  | 2026-11-05 |  |  |  |  | 12760472816
|  |  |  | 2026-08-17 to 2026-11-05 |  |  |  | 0/84